## Sheet1
|  | actions | owner | partition | noted
W1 | Day 1 | Meeting Mentor, PM (introduce/ Q&A) | mentor | mentee, PM | Mentor provide documents
|  | set up ENV | mentee
| Day 2 | Overview Technical: Java, springboot, micro service | mentor | mentee | Mentor provide documents
Write a short paragraph to introduce myself, ..
|  | Mentor provide request | mentor | mentee | + tools : intellij + db: + Maven, sdk 11 + Follow micro Service
| Day 3 | Meeting mentor, show REQ, metor provide feedback | mentor | mentee
Define ERD
| Day 4 | Build on Service (DB service): connect DB and define controler/facade/service/repository | mentee
| Day 5 | Continue practice + report to mentor | mentee
W2 | Day 1+ 2 + 3 | Work breakdown & estimation for requirements | mentee
| Day 3 + 4 | Report WBS. Write technical document describe the implement. | mentee
| Day 5 | Demo + report to mentor | mentee
W3 | Day 1+ 2 | Research & apply Spring cloud gateway & microservice | mentee
| Day 3 | Research & apply Swagger to generate API
| Day 4 | Practice to connect FE (UI + BE) | mentee
| Day 5 | Demo + report to mentor | mentee
W4 | Day 1 -> 4 | Complete implementation | mentee
| Day 5 | BIG demo | mentee |  | get feedback + decide to continue learning or not
W5 | Day 1 + 2 | Scheduler for background task
| Day 3 + 4 | Research and implement MQ | mentee
| Day 5 | Demo + report to mentor | mentee
W6 | Day 1+ 2 | Generate report PDF/excel file | mentee
| Day 3 | Research & apply Aspect programming | mentee
| Day 4+5 | Demo + report to mentor | mentee
W7 | Day 1 + 2 | Jmeter | mentee
| Day 3 + 4 | Non functional requirement: logging & performance | mentee
W8 | Day 1 -> 4 | Complete implement & design document + Q&A | mentee
| Day 5 | Final Demo | mentee